## Project breif
Project Goal: The goal of this project is to use Rasberry Pi and AWS to deploy a serverless Image recognition application.
Objectives: | 1. Taking picture from rasberry Pi and automatically upload it to AWS S3
2. Using AWS Lambda to invoke AWS Rekognition service to detect labels from the image
3. Store Labels and other image data into DynamoDB
4. Present the result back to the end user

## Team structure
Project Management | Mou | Prashant
Solution Architect | Akash | Narinder
Developer | Mou | Hassan | Matangi | Mayowa
Testing | Michael
DevOps | Akash | Nemiya | Michael
Database | Koko
IoT | Andrejz | Robert
Alexa | Jyothyraj | Mrudula | Aloysius
SCRUM, Project control | Narinder

## Project plan
Starting date | 2021-05-24
Deadline | 2021-06-27
Days left | 34
Task | Team/Lead | Estimated time (Days) | Starting date | Deadline | Progress | Updated Deadline
Project Phase 1
Design Document | Akash/Narinder | 7 | 2021-06-05 | 2021-06-12 | 15% | 2021-06-12 03:36
Rasberry Pi | Andrejz/Robert | 14 | 2021-05-22 | 2021-06-05 | 100% | 2021-06-06
AWS Lambda | Hassan/Mou | 14 | 2021-05-22 | 2021-06-05 | 85% | 2021-05-06
Database | Koko | 7 | 2021-06-05 | 2021-06-12 | 0% | 2021-06-12
Alexa | Jyothi | 7 | 2021-06-05 | 2021-06-12 | 10% | 2021-06-12 02:24
Project Phase 2
AWS Lambda 2 | Hassan/Mou | 6 | 2021-06-07 | 2021-06-13
Testing 1 | Michael/Nemiya | 7 | 2021-06-05 | 2021-06-12
Rasberry Pi Ph 2 (activated by Motion sensor) | Robert/Andejz | 7 | 2021-06-05 | 2021-06-12
Project Management | Mou | Prashant
Solution Architect | Akash | Narinder
Developer | Mou | Hassan | Matangi | Mayowa
Testing | Michael
DevOps | Akash | Nemiya | Michael
Database | Koko
IoT | Andrejz | Robert
Alexa | Jyothyraj | Mrudula | Aloysius
SCRUM, Project control | Narinder
Formulas:
Deadline = IFERROR(IF(INT([Estimated time (Days)]) > 0, [Starting date]+[Estimated time (Days)], "TBD"), "")
Updated Deadline = IFERROR(IF(INT([Deadline]) > 0, [Progress]+[Deadline], "TBD"), "")